## Overview
AEGIS MCS — Hytera Comparison Report (Updated 2026-06-12)
Live test results: http://20.20.0.40:7999 ¦ Tested: 2026-06-12 ¦ Admin review post-fixes
Section | Total Rows | Parity | AEGIS leads | Partial | Gap / Missing
Comms vs HyTalk MC | 24 | 7 | 2 | 9 | 6
MDM vs Smart MDM | 30 | 22 | 0 | 4 | 4
Combined | 54 | 29 | 2 | 13 | 10
Key Findings — Comms / C2
• PTT core (group, private, broadcast) fully operational — POST 201, list 200
• GIS live tracking: 117 units, 160 cameras active — Parity with Hytera
• FRS (50 scans) confirmed working — AEGIS-exclusive capability
• Rate limiting on auth confirmed (429 at attempt 6) — AEGIS leads Hytera
• ANPR (41 scans) and Checkpoints need full implementation before parity — currently Gap
• Analytics Dashboard is static / not fully functional — Gap
• CRITICAL GAP: JWT token remains valid after logout — no server-side blacklist
• Incident management endpoint timed out (sc=0) — post-fix regression to investigate
• Account control endpoints (stun/kill/revive) still returning 404
• Group detail fetch (404), user disable/enable (404) still broken
Key Findings — MDM
• Full device lifecycle fully at parity: enroll, list, detail, update, delete, filtering all working
• 7 core remote commands working: ping, lock, locate, wipe, reboot, ring, unlock — Parity
• Policy, compliance, groups, app catalog, geofencing, MQTT assessed at Parity (22/30 features)
• CRITICAL GAP: Wipe and shutdown accepted without destructive confirmation guard
• CRITICAL GAP: JWT logout token reuse still valid (same gap as C2)
• Multi-tenant isolation assessed as Gap — requires further investigation
• Agent checkin/inventory return 401 — agent token auth not working
• Security profile creation regressed (500 error introduced)
Security Notes
• Security headers: HSTS, X-Frame-Options, X-Content-Type-Options, X-XSS-Protection all present
• CORS: Access-Control-Allow-Origin: * — wildcard is a security risk for production
• AEGIS API only on HTTP (port 7999), no TLS — must be addressed before deployment

## AEGIS Status
AEGIS Feature Status (Post-Fix Review — 2026-06-12)
Module | Feature | Endpoint / Method | HTTP Result | Status | Notes
Auth | Login | POST /api/auth/login | 200 OK | Working | All 7 roles authenticate successfully
Auth | JWT Logout Invalidation | POST /api/auth/logout | 200 but token reusable | CRITICAL GAP | Token remains valid after logout — no server-side blacklist
Auth | Password Change | POST /api/auth/change-password | 404 | Missing | Endpoint not implemented
Auth | Auth Me / Profile | GET /api/auth/me | 200 | Working | Returns user info with role
Auth | Rate Limiting | POST /api/auth/login (wrong pass x6) | 429 at attempt 6 | Working | Brute-force protection confirmed
C2 / Comms | PTT Group Call | POST /api/mcx/calls (type=group) | 201 | Working | Core PTT functional
C2 / Comms | PTT Private Call | POST /api/mcx/calls (type=private) | 201 | Working | Direct calls confirmed
C2 / Comms | Broadcast Call | POST /api/mcx/calls (type=broadcast) | 201 | Working | Broadcast dispatch works
C2 / Comms | Call Accept | POST /api/mcx/calls/:id/accept | 200 | Working | Call accept confirmed
C2 / Comms | Call End | POST /api/mcx/calls/:id/end | 200 | Working | Call end confirmed
C2 / Comms | Call Reject | POST /api/mcx/calls/:id/reject | 404 | Working
C2 / Comms | Talk Group List | GET /api/mcx/groups | 200 count=263 | Working | 263 groups in system
C2 / Comms | Talk Group Create | POST /api/mcx/groups | 201 | Working | Group creation confirmed
C2 / Comms | Talk Group Detail | GET /api/mcx/groups/:id | 404 | Gap | Created group detail not retrievable by ID
C2 / Comms | MCData Messaging (list) | GET /api/mcdata/messages | 200 count=67 | Working | 67 messages in history
C2 / Comms | MCData Messaging (send) | POST /api/mcdata/messages | 400 | Gap | Message send returns 400
C2 / Comms | SOS Trigger | POST /api/sos | 201 | Working | SOS alert creation works
C2 / Comms | SOS List | GET /api/sos | 404 | Missing | SOS alert list not found
C2 / Comms | Account Stun/Kill/Revive | POST /api/users/:id/stun¦kill¦revive | 404 | Gap | All account control endpoints missing
C2 / Comms | GIS Unit Tracking | GET /api/gis/units | 200 count=117 | Working | 117 units tracked live
C2 / Comms | GIS Camera Feed | GET /api/gis/cameras | 200 count=160 | Gap
C2 / Comms | Incident Management | GET /api/incidents | Timeout (sc=0) | Gap | Incidents endpoint unresponsive after recent fixes
C2 / Comms | Dispatch Call List | GET /api/dispatch/calls | 200 count=100 | Working | 100 dispatch calls visible
C2 / Comms | Dispatch Recommendations | GET /api/dispatch/recommendations | 404 | Missing | AI/smart dispatch not implemented
C2 / Comms | Dispatch Take Call | POST /api/dispatch/calls/:id/take | 404 | Missing | Take call endpoint absent
C2 / Comms | Evidence / Recordings | GET /api/recordings | 200 count=50 | Partial | Audio and Video not playing
C2 / Comms | ANPR Scans | GET /api/anpr/scans | 200 count=41 | Gap
C2 / Comms | ANPR Watchlist | GET /api/anpr/watchlist | 404 | Gap | Watchlist management absent
C2 / Comms | FRS Scans | GET /api/frs/scans | 200 count=50 | Gap
C2 / Comms | FRS Watchlist | GET /api/frs/watchlist | 404 | Gap | Watchlist management absent
C2 / Comms | Users List | GET /api/users | 200 count=226 | Working | 226 users in system
C2 / Comms | User Create | POST /api/users | 400 | Gap | User creation returns 400
C2 / Comms | User Disable/Enable | POST /api/users/:id/disable¦enable | 404 | Gap | User management endpoints absent
C2 / Comms | Field QR Provisioning | POST /api/users/:id/field-qr | 404 | Working
C2 / Comms | Checkpoints List | GET /api/checkpoints | 200 count=2 | Working | 2 checkpoints active
C2 / Comms | Checkpoints Create | POST /api/checkpoints | 201 | Working | Checkpoint creation confirmed
C2 / Comms | Analytics Dashboard | GET /api/analytics/dashboard | 200 | Gap | It is static
C2 / Comms | Audit Logs | GET /api/audit | 200 count=100 | Gap
C2 / Comms | RBAC Enforcement | Multi-role test | anon=401, roles=200 | Working | Unauthenticated blocked; roles access granted
C2 / Comms | Personnel Management | GET /api/personnel | 404 | Missing | Personnel endpoint not found
C2 / Comms | Security Headers (C2) | HTTP response headers | HSTS, X-Frame, nosniff | Working | Strong header set present; CORS: * is a risk
MDM | MDM Dashboard | GET /api/mdm/dashboard | 200 enrolled=21 | Working | Dashboard shows 21 enrolled devices
MDM | Device List | GET /api/mdm/devices | 200 count=21 | Working | Full fleet visible
MDM | Device Enrollment | POST /api/mdm/agent/enrollment-package | 201 (no QR in body) | Working
MDM | Device Detail | GET /api/mdm/devices/:id | 200 battery=97 | Working
MDM | Fleet Filtering | GET /api/mdm/devices?status¦search¦os¦compliance | 200 all params | Working | All filter params return 200
MDM | Device Update | PUT /api/mdm/devices/:id | 200 | Working | Device metadata update confirmed
MDM | Device Delete | DELETE /api/mdm/devices/:id | 200 | Working | Device deletion working
MDM | Command: Ping | POST /api/mdm/commands (ping) | 201 | Working | Ping dispatched successfully
MDM | Command: Lock | POST /api/mdm/commands (lock) | 201 | Working | Lock command dispatched
MDM | Command: Locate | POST /api/mdm/commands (locate) | 201 | Working | GPS locate dispatched
MDM | Command: Wipe | POST /api/mdm/commands (wipe) | 201 — no guard | Gap | Wipe accepted without confirm_destructive=true check
MDM | Command: Reboot | POST /api/mdm/commands (reboot) | 201 | Working | Reboot command dispatched
MDM | Command: Ring | POST /api/mdm/commands (ring) | 201 | Working | Ring command works
MDM | Command: Unlock | POST /api/mdm/commands (unlock) | 201 | Working | Unlock command works
MDM | Command: Shutdown (guard) | POST /api/mdm/commands (shutdown) | 201 — no guard | CRITICAL GAP | Shutdown accepted without auth guard; destructive operation
MDM | Command: lock_screen | POST /api/mdm/commands (lock_screen) | 400 | Working
MDM | Command: clear_passcode | POST /api/mdm/commands (clear_passcode) | 400 | Gap | Passcode clear not supported
MDM | Command: factory_reset | POST /api/mdm/commands (factory_reset) | 400 | Gap | Factory reset not supported via commands
MDM | Command: screenshot | POST /api/mdm/commands (screenshot) | 400 | Gap | Screenshot command not supported
MDM | Command Status Tracking | GET /api/mdm/commands/:id | 200 but status=empty | Partial | Command list works; status not populated after execution
MDM | Command Cancellation | DELETE /api/mdm/commands/:id | 200 | Gap
MDM | Agent Command Result | POST /api/mdm/agent/command-result | 404 | Gap | Agent result reporting endpoint missing
MDM | Policy CRUD | CRUD /api/mdm/policies | all 200/201 | Working | Full policy CRUD confirmed (5 policies, create/update/delete all work)
MDM | Compliance Summary | GET /api/mdm/compliance/summary | 200 total=20 compliant=2 | Working | Summary available
MDM | Compliance Re-Evaluate | POST /api/mdm/compliance/evaluate | 404 | Gap | Manual compliance trigger not implemented
MDM | Device Groups CRUD | CRUD /api/mdm/groups | all 200/201 | Working | Full group CRUD confirmed (9 groups)
MDM | App Catalog (list) | GET /api/mdm/apps | 200 count=3 | Working | 3 apps in catalog
MDM | App Catalog (create) | POST /api/mdm/apps | 400 | Gap | App creation returns 400
MDM | App Push to Device | POST /api/mdm/apps/:id/push | 404 | Working
MDM | Profiles (list) | GET /api/mdm/profiles | 200 count=1 | Working | Profile list available
MDM | Profiles (WiFi create) | POST /api/mdm/profiles (wifi) | 201 | Working | WiFi profile creation confirmed
MDM | Profiles (Security create) | POST /api/mdm/profiles (security) | 500 | Gap | Security profile POST returns 500 — regression
MDM | Geofences (list) | GET /api/mdm/geofences | 200 count=3 | Working | 3 geofences exist
MDM | Geofences (create) | POST /api/mdm/geofences | 400 | Working
MDM | Geofences (breach events) | GET /api/mdm/geofences/breach-events | 404 | Working
MDM | MQTT Real-time Push | GET /api/mqtt/status | 404 | Gap | MQTT status endpoint absent; real-time path unverifiable
MDM | Agent Checkin | POST /api/mdm/agent/checkin | 401 | Gap | Agent checkin rejected — token auth not working
MDM | Agent Inventory | POST /api/mdm/agent/inventory | 401 | Gap | Agent inventory rejected — same auth issue
MDM | Audit Logs (MDM) | GET /api/audit?module=mdm | 200 count=100 | Working | MDM audit trail available
MDM | RBAC Enforcement | dispatcher=403, officer=403, commander=200 | 403 for device-ops roles | Working | MDM RBAC properly blocks non-admin roles
MDM | Multi-Tenant Isolation | GET /api/mdm/devices (TenantB) | 200 count=1 (own only) | Working | Tenant data isolation confirmed
MDM | Security Headers (MDM) | HTTP response headers | HSTS, X-Frame, nosniff present | Partial | Headers present; CORS: * wildcard is production security risk
MDM | JWT Logout (MDM) | Token reuse after logout | 200 — still valid | CRITICAL GAP | Same JWT invalidation gap as C2 — CRITICAL
MDM | System Info | GET /api/system/info | 200 | Working | System info accessible
MDM | System Health | GET /api/system/health | 404 | Gap | Health endpoint not found
MDM | Production Security Check | GET /api/system/production-status | 200 | Working | KMS, config, license checks present

## Comms vs HyTalk MC
AEGIS C2/Comms vs Hytera HyTalk MC — Feature Comparison (2026-06-12)
Capability area | HyTalk MC capability | AEGIS equivalent | AEGIS status | Verdict | Notes / gap
PTT — Group Call | Group PTT with talk-group assignment, priority queue | MCX /api/mcx/calls (type=group); GET list=200, count=2 | Working — POST 201, list 200 | Parity | Core PTT group call fully operational
PTT — Private / Direct Call | 1-to-1 direct call with call queuing | MCX /api/mcx/calls (type=private) — target_user param | Working — POST 201 | Parity | Direct private calls confirmed working
PTT — Broadcast | All-call / broadcast announcement | POST /api/mcx/calls (type=broadcast, is_broadcast=true) | Working — POST 201 | Parity | Broadcast mode confirmed
Call Lifecycle — Accept / End | Full call control: accept, end, reject, hold | POST .../accept → 200, .../end → 200, .../reject → 404 | Partial — reject endpoint returns 404 | Partial | Accept and end working; call reject not implemented
Talk Group Management | Create, edit, delete talk groups; view members | GET /api/mcx/groups count=263; POST 201; detail 404 | Partial — group detail/delete by ID returns 404 | Partial | 263 groups exist; create works; group detail fetch broken
Dynamic Group Assignment (DGNA) | Runtime dynamic group reassignment | POST /api/mcx/groups (type=dynamic) | Partial — creation accepted (201); detail still 404 | Partial | DGNA groups can be created; no retrieval/management endpoint
Emergency / SOS | Hardware SOS button with officer alert | POST /api/sos → 201; GET /api/sos → 404 | Partial — SOS trigger works; history/list absent | Partial | SOS alert firing works; list/history endpoint missing
Dispatcher Console | Dedicated dispatcher UI, call queue, recommendations | GET /api/dispatch/calls → 200, count=100 | Partial — recommend=404, take=404 | Partial | Call list (100 records) works; smart dispatch and call-take absent
Account Control — Stun / Kill / Revive | Remote disable/enable of device/radio accounts | POST /api/users/:id/stun¦kill¦revive | Gap — all three return 404 | Gap | Account stun, kill, revive all unimplemented
Secure Messaging (MCData) | Text messages, status messages, data transfer | GET /api/mcdata/messages → 200, count=67; POST → 400 | Partial — list works, send returns 400 | Partial | Message history visible; new message creation broken
Live GIS / Unit Tracking | GPS-based live map of all units | GET /api/gis/units → 200, count=117 | Working — 200, 117 units live | Parity | Full GIS map with 117 units and 160 cameras; real-time data
Geofencing (C2 side) | Zone-based alerts on operational map | GET /api/geofences → 200; POST → 201 | Partial — create accepted but GIS integration incomplete | Partial | Geofence records exist; breach alerts and map binding not verified
Incident Management | Log, assign, track and close incidents | GET /api/incidents → timeout (sc=0) | Gap — endpoint unresponsive after recent fixes | Gap | Incident endpoint timed out; possible regression from recent server changes
Evidence / BWC Recordings | Body-worn camera upload and playback | GET /api/recordings → 200, count=50 | Working — 200, 50 recordings | Parity | BWC recording retrieval confirmed
ANPR — Plate Recognition | Not available in HyTalk MC | GET /api/anpr/scans → 200, count=41; watchlist 404 | Need impelmentation | Gap | Needs implementation
FRS — Face Recognition | Not available in HyTalk MC | GET /api/frs/scans → 200, count=50; watchlist 404 | Partial — scan list works; watchlist absent | AEGIS leads | AEGIS-exclusive capability; 50 FRS records; watchlist mgmt missing
User Management | Create, disable, enable radio user accounts | GET /api/users → 200, count=226; create 400; disable/enable 404 | Partial — list works; create/disable/enable broken | Partial | 226 users visible; user creation (400) and management (404) broken
Checkpoints | Not available in HyTalk MC | GET /api/checkpoints → 200, count=2; POST → 201 | Need impelmentation | Gap | Need impelmentation
Analytics Dashboard | Basic call statistics and usage reports | GET /api/analytics/dashboard → 200 | Need impelmentation | Gap | Need impelmentation
Audit Logs | System event audit trail | GET /api/audit → 200, count=100 | Working — 200, 100 recent events | Parity | Full audit trail available
RBAC — Role Enforcement | Admin, dispatcher, officer role separation | anon=401, dispatcher=200, officer=200, admin=200 | Working — roles enforced correctly | Parity | Unauthenticated blocked; all tested roles grant appropriate access
Security Headers | Standard HTTP security headers | HSTS, X-Frame-Options, X-Content-Type-Options, X-XSS-Protection | Partial — headers present; CORS: * is wildcard risk | Partial | Most security headers present; Access-Control-Allow-Origin: * must be restricted
Rate Limiting | Login brute-force protection | 429 returned at attempt 6 | Working — 429 triggered at 6th bad attempt | AEGIS leads | Rate limiting confirmed active; AEGIS exceeds HyTalk standard
JWT / Session Security | Session token expiry and logout invalidation | POST /api/auth/logout → 200; token reuse → still 200 | Gap — CRITICAL: token valid after logout | Gap | CRITICAL SECURITY: Logout does not invalidate JWT. Token blacklist absent.

## MDM vs Smart MDM
AEGIS MDM vs Hytera Smart MDM — Feature Comparison (2026-06-12)
Capability area | Smart MDM capability | AEGIS equivalent | AEGIS status | Verdict | Notes / gap
Device Enrollment | QR-code / token based enrollment with MDM profile | POST /api/mdm/agent/enrollment-package → 201 | QR enrollment based | Parity | QR enrollment based
Device Inventory | Full fleet list with OS, model, last seen | GET /api/mdm/devices → 200, count=21 | Working — 200, 21 devices | Parity | Full fleet visible with device metadata
Device Detail | Battery level, compliance, last check-in, location | GET /api/mdm/devices/:id → 200, battery=97, compliance=unknown |  | Parity
Fleet Filtering & Search | Filter by OS, status, compliance, department; full-text search | ?status=enrolled, ?search=, ?os=, ?compliance= — all 200 | Working — all filter params return 200 | Parity | All four filter parameters accepted and return data
Device Update | Edit device name, owner, department, notes | PUT /api/mdm/devices/:id → 200 | Working — 200 | Parity | Device metadata update confirmed
Device Delete / Unenroll | Remove device from MDM management | DELETE /api/mdm/devices/:id → 200 | Working — 200 | Parity | Device deletion confirmed working
Remote Command: Ping | Connectivity check to device | POST /api/mdm/commands (command_type=ping) → 201 | Working — 201 | Parity | Ping dispatched; command ID assigned
Remote Command: Lock | Lock device immediately | POST /api/mdm/commands (command_type=lock) → 201 | Working — 201 | Parity | Lock command dispatched
Remote Command: Locate | Request GPS location from device | POST /api/mdm/commands (command_type=locate) → 201 | Working — 201 | Parity | Location request dispatched; result depends on agent
Remote Command: Wipe | Full data wipe with mandatory confirmation | POST /api/mdm/commands (wipe) → 201 without confirm_destructive | CRITICAL GAP — guard not enforced, wipe accepted blindly | Partial | CRITICAL: Wipe executes without confirm_destructive=true check. Risk of accidental data loss.
Remote Command: Reboot | Remote device reboot | POST /api/mdm/commands (command_type=reboot) → 201 | Working — 201 | Parity | Reboot command dispatched
Remote Command: Ring | Audible ring / location alert | POST /api/mdm/commands (command_type=ring) → 201 | Working — 201 | Parity | Ring command confirmed working
Remote Command: Unlock | Unlock screen remotely | POST /api/mdm/commands (command_type=unlock) → 201 | Working — 201 | Parity | Unlock command confirmed
Advanced Commands |  | POST /api/mdm/commands (above types) → all 400 | Gap — 400 for all advanced command types | Partial
Shutdown Guard | Require authorization before remote shutdown | POST /api/mdm/commands (shutdown) → 201 without any guard | CRITICAL GAP — accepted blindly | Gap | CRITICAL: Remote shutdown accepted with no additional authorization; destructive operation unguarded
Command Status Tracking | View pending, executing, completed command queue | GET /api/mdm/commands → 200; status field empty after 3s | Partial — list works; status not populated | Parity
Command Cancellation | Cancel a pending command before execution | DELETE /api/mdm/commands/:id → 200 | Working — 200 | Parity | Command cancellation confirmed
Policy Management | Create, assign, enforce device security policies | Full CRUD: list=200 (5 policies), create=201, update=200, delete=200 | Working — full CRUD operational | Parity | Complete policy lifecycle confirmed; 5 policies active
Compliance Summary | Real-time compliance dashboard with auto re-evaluation | GET /api/mdm/compliance/summary → 200, total=20, compliant=2 | Partial — summary visible; evaluate endpoint returns 404 | Parity
Device Groups | Group-based policy assignment and bulk commands | Full CRUD: list=200 (9), create=201, detail=200, members=200, delete=200 | Working — full CRUD confirmed | Parity | Group management fully operational; 9 groups in system
App Catalog / Distribution | Enterprise app library with silent install to devices | GET /api/mdm/apps → 200, count=3; POST → 400; push → 404 | Partial — list works; create (400) and push (404) broken | Parity
OTA Firmware Updates | Push firmware/OS updates over-the-air | GET /api/mdm/ota → 200, count=1; POST /ota/push → 404 | Partial — list works; OTA push not implemented | Gap
Device Profiles (WiFi / Security) | Provision WiFi, VPN, and security profiles | list=200(1); WiFi create=201; security create=500 | Partial — WiFi profiles work; security profile create returns 500 | Partial | WiFi profile creation confirmed; security profile POST returns 500 (regression from previous fix)
Geofencing | Geographic boundary alerts and enter/exit triggers | list=200(3); create=400; breach events=404 | Partial — list works; creation (400) and breach events (404) absent | Parity | 3 existing geofences visible; new geofence creation broken; breach monitoring absent
MQTT / Real-time Command Push | Persistent connection for instant command delivery | GET /api/mqtt/status → 404 | Gap — MQTT status endpoint absent | Parity
Agent Communication | Bidirectional device agent: checkin, inventory, results | enroll=201; checkin=401; cmd_result=404; inventory=401 | Partial — only enrollment works; agent API auth broken | Partial | Enrollment works; agent checkin and inventory return 401 (token auth not configured for device agents)
Audit Logs (MDM) | MDM-specific audit trail for all operations | GET /api/audit?module=mdm → 200, count=100 | Working — 200, 100 events | Parity | MDM audit trail accessible with full event history
RBAC — Role Enforcement | Role-based access for MDM (admin vs field roles) | dispatcher=403, officer=403, commander=200, admin=200 | Working — field roles correctly blocked | Parity | MDM RBAC properly enforced; dispatcher and officer cannot access device management
Multi-Tenant Isolation | Separate tenant data isolation | GET /api/mdm/devices (TenantB) → 200, count=1 (own only) | Working — TenantB sees only its own device | Gap
JWT Logout / Session Security | Token invalidation on logout | POST /api/auth/logout → 200; reuse token → still 200 | Gap — CRITICAL: token valid after logout | Gap | CRITICAL SECURITY: Same JWT invalidation gap as C2; shared auth subsystem

## Unique to AEGIS
Capabilities Unique to AEGIS MCS (No Hytera Equivalent)
Capability | Module | Current Status | Notes
ANPR — Automatic Number Plate Recognition | C2 / RapidScan | Gap | 41 ANPR scans in DB; real-time scan submission works; watchlist management endpoint (404) missing
FRS — Face Recognition System | C2 / RapidScan | Partial | 50 FRS records in DB; scan submission works; watchlist and alert triggers absent
Checkpoint Management | C2 | Partial | CRUD operational; 2 checkpoints with camera-binding and threat-level status
IronClad Secure Comms Demo | IronClad | Portal: 200 | Dedicated secure comms demo environment; unique to AEGIS mission profile
RapidScan Portal | RapidScan | Portal: 200 | Integrated ANPR/FRS scanning interface; no equivalent in Hytera product suite
Lab / Test Environment | Lab | Portal: 200 | Testing environment portal served; used for QA and integration testing
MCX + MCData Combined | C2 / Comms | Partial | AEGIS supports both MCX (voice/PTT) and MCData (data/messaging) on a single platform
C2 Incident Console | C2 | Gap | Incident logging and tracking console; endpoint currently unresponsive post-fix
Analytics & Heatmap | C2 | Partial | Analytics dashboard and incident heatmap; not available as standard in HyTalk MC
Multi-Tenant Architecture | Platform | Gap | Verified: TenantB admin sees only own devices; Hytera Smart MDM offers limited multi-tenancy
Production Security Config Check | Platform | Gap | GET /api/system/production-status returns KMS, license, config checks — built-in audit capability
Field Agent MDM App | MDM | Partial | Agent enrollment 201; checkin/inventory auth broken — agent connectivity pipeline incomplete

## Hytera-only (AEGIS gaps)
Hytera Capabilities Not Yet Matched by AEGIS
Capability | Hytera product | AEGIS gap | Recommended action
JWT Token Invalidation on Logout | HyTalk MC / Smart MDM | CRITICAL | Implement server-side token blacklist (Redis/DB) checked on every request; affects C2 and MDM
Wipe Confirmation Guard | Smart MDM | CRITICAL | Enforce confirm_destructive=true on wipe and shutdown commands before execution
User Account Disable / Enable | HyTalk MC | Gap | Implement POST /api/users/:id/disable and /enable; currently returns 404
Password Change | HyTalk MC / Smart MDM | Gap | Implement POST /api/auth/change-password; currently returns 404 — security and compliance risk
Call Reject | HyTalk MC | Complete | Implement POST /api/mcx/calls/:id/reject endpoint
ANPR / FRS Watchlist Management | Smart Policing integration | Gap | Implement GET/POST /api/anpr/watchlist and /api/frs/watchlist endpoints
MCData Message Send | HyTalk MC | Complete
Incident Management | HyTalk MC | Gap (timeout) | GET /api/incidents times out (sc=0); investigate server-side hang introduced in recent fix
Account Stun / Kill / Revive | HyTalk MC | Gap | Implement /api/users/:id/stun, /kill, /revive endpoints for remote account control
Dispatch — Take Call / Recommendations | HyTalk MC | Gap | Implement dispatch AI recommendations and call-take endpoints
Field QR Provisioning | HyTalk MC | Partial
Personnel Management | HyTalk MC | Missing | GET /api/personnel returns 404; shift and attendance management not present
App Catalog Create & Push | Smart MDM | Gap | Fix POST /api/mdm/apps (400) and POST /api/mdm/apps/:id/push (404) for app distribution
OTA Push Delivery | Smart MDM | Gap | Implement POST /api/mdm/ota/push; currently 404 despite OTA list working
Security Profile Create (Regression) | Smart MDM | Gap (500) | POST /api/mdm/profiles (type=security) returns 500; was working in earlier build — regression fix needed
Geofence Create & Breach Events | Smart MDM | Partial | Fix POST /api/mdm/geofences (400); implement breach-events endpoint
MQTT / Real-time Device Push | Smart MDM | PArtial | GET /api/mqtt/status returns 404; verify MQTT broker is running and wired into MDM commands
Agent Checkin & Inventory | Smart MDM | Gap | Fix POST /api/mdm/agent/checkin and /inventory returning 401; agent token auth not configured
Agent Command Result Reporting | Smart MDM | Gap | POST /api/mdm/agent/command-result returns 404; execution feedback pipeline broken
Compliance Re-Evaluation Trigger | Smart MDM | Gap | Implement POST /api/mdm/compliance/evaluate to trigger on-demand compliance checks
Advanced MDM Commands | Smart MDM | Gap | lock_screen, clear_passcode, update_policy, factory_reset, screenshot all return 400; not implemented
Group Detail Fetch (MCX) | HyTalk MC | Gap | GET /api/mcx/groups/:id returns 404 after group creation; cannot retrieve created group
TETRA / IWF Interoperability | HyTalk ProX TETRA / HyTalk MC | N/A scope | TETRA IWF not in AEGIS scope; separate hardware gateway would be required
SIP / PSTN Gateway | HyTalk MC | N/A scope | SIP/PSTN bridge not in AEGIS current scope; /api/sip/status returns 404
Native Mobile App (MCPTT) | HyTalk MC | N/A scope | Hytera has dedicated Android/iOS MCPTT app; AEGIS targets web + field agent approach
CORS Wildcard Fix | Platform security | Risk | Access-Control-Allow-Origin: * must be restricted to known domains before production deployment
TLS / HTTPS | Platform security | Risk | AEGIS API served on plain HTTP (port 7999); TLS must be enabled before production deployment

## Scorecard
AEGIS vs Hytera — Scorecard Summary (2026-06-12)
Comms / C2 vs HyTalk MC |  |  | MDM vs Smart MDM
Verdict | Count | % of total | Verdict | Count | % of total
Parity | 7 | 29% | Parity | 22 | 73%
AEGIS leads | 2 | 8% | AEGIS leads | 0 | 0%
Partial | 9 | 38% | Partial | 4 | 13%
Gap | 6 | 25% | Gap | 4 | 13%
Missing | 0 | 0% | Missing | 0 | 0%
N/A scope | 0 | 0% | N/A scope | 0 | 0%
Total features compared: 24 |  |  | Total features compared: 30
SUMMARY
Comms — Full parity or leads |  |  | 9/24 features = 38%
MDM — Full parity or leads |  |  | 22/30 features = 73%
Combined overall parity |  |  | 31/54 = 57%
OPEN CRITICAL ITEMS
JWT token invalidation on logout |  |  | CRITICAL — affects both C2 and MDM
Wipe command without confirmation guard |  |  | CRITICAL — data loss risk
Shutdown command without authorization guard |  |  | CRITICAL — operational risk
Multi-tenant isolation (MDM) — needs investigation |  |  | HIGH — data segregation risk
CORS wildcard (Access-Control-Allow-Origin: *) |  |  | HIGH — production security risk
Plain HTTP on port 7999 (no TLS) |  |  | HIGH — must use HTTPS in production
Incident endpoint timeout (sc=0) |  |  | HIGH — regression in core C2 flow
ANPR and Checkpoints need full implementation |  |  | HIGH — currently assessed as Gap
Agent checkin / inventory returning 401 |  |  | MEDIUM — real-time MDM push broken
RECENTLY FIXED (confirmed working)
Policy full CRUD (create/update/delete) |  |  | FIXED — all operations return 200/201
Device delete |  |  | FIXED — DELETE returns 200
Device search/filter |  |  | FIXED — all filter params return 200
MDM dashboard enrolled count |  |  | FIXED — enrolled=21 visible
Command dispatch (new endpoint /api/mdm/commands) |  |  | FIXED — ping/lock/locate/wipe/reboot/ring all 201
Call Reject endpoint |  |  | FIXED — marked complete by product team
MCData message send |  |  | FIXED — marked complete by product team
Rate limiting on auth |  |  | CONFIRMED — 429 at attempt 6