## Sheet1
Category | Sr. No. | Feature | Status as of 24.06.2026 | Updated Remarks | Status as of 7/1/2026
Real-Time Dispatch | 1 | Video and voice pull | Only Video Pull (Voice Pull needs explanation?) |  | Pull Request with acceptance working. We test on 2 devices and it's working
| 2 | Remote snapshot | Needs Further Explanation | Control room can remotely take a picture from the BWC camera | Not Developed
| 3 | Remote voice recording | Needs Further Explanation | Control room can remotely start audio recording on the BWC. | Not Developed
| 4 | Remote video recording | Needs Further Explanation | Control room can remotely start/stop video recording on the BWC. | Not Developed
| 5 | Remote playback | Needs Further Explanation | Control room can play recorded files remotely from device or server. | Not Developed
| 6 | Audio and video file query | Needs Further Explanation | Operator can search recorded audio/video files by date, device, officer, event, etc. | Working. UI/UX Improvement required
Trunking Communications | 7 | PTT (Push-to-Talk) call | Yes |  | Not Working on VW on orientation change. Disoration detetced
| 8 | Instant messaging | Yes |  | Search functionality implemeted in every dropdown. Not working on VWC. Unable to identify that which message is sent and which message is received
Positioning Management | 9 | Real-time positioning | Yes |  | Working.
| 10 | Historical track | No |  | Not Developed
| 11 | Route planning | Yes |  | Not Working
| 12 | GEO fence | Yes |  | Not able to test due to internet connectivity
Device Management | 13 | Basic device information | Yes |  | Working
| 14 | Parameter modification | Needs Further Explanation | Changing device settings remotely, such as quality, GPS, recording, upload mode, etc | Not Developed
| 15 | Acquisition settings | Needs Further Explanation | Settings related to capturing/uploading evidence like video, audio, photo, storage, etc. | Not Developed
| 16 | Watermark | No |  | Not Working
| 17 | Online/offline presence | Yes |  | Working
| 18 | Time synchronization | Yes |  | Not Developed
| 19 | Alarm management | Yes (Needs specific alarms) |  | Not Developed
| 20 | Remote device status check | Yes |  | Working
Alarm & Safety | 21 | Emergency alarm | Yes |  | On view incident, instead of redirect me to the specific incident, it redirects to the grid
| 22 | Camera block alarm | Yes |  | Not Working
| 23 | Man down detection | No |  | Not developed
Integrations & Compatibility | 24 | ONVIF protocol support | No |  | Understanding required
| 25 | RTSP protocol support | Yes |  | Understanding required
| 26 | 3G / LTE / WLAN network access | Yes |  | Understanding required
| 27 | Face recognition integration | Yes |  | Partially Developed
| 28 | Digital evidence management integration | Yes |  | Working
| 29 | CCTV integration | Yes |  | Working
| 30 | Up to 50-path concurrent video pull | Yes (Needs Verification) |  | Part of Stress testing
| 31 | Up to 1,000 connected devices on a single server | Yes (Needs Verification) |  | Part of Stress testing
| 32 | Up to 1,000 clients on a single server | Yes (Needs Verification) |  | Part of Stress testing
| 33 | Up to 200 concurrent videos | Yes (Needs Verification) |  | Part of Stress testing
| 34 | Public, private, or LAN deployment support | Yes |  | Pending